## Overview
Task_ID | Category | Module | Task_Name | Task_Description | Subtasks | Priority | Dependencies | Blockers | Risk_Level | Review_Type | Acceptance_Criteria | HIPAA_Relevant | Is_Milestone | Notes | Start_Date | Target_Date | Completion_Date | Percent_Complete
W1-D1-01 | Infrastructure | Database | Install SQL Server | Install SQL Server on deployment server and create aqtracker database | 1. Download and install SQL Server; 2. Create aqtracker database; 3. Create service account for FastAPI; 4. Verify server is running and accessible | P0-Critical | None |  | Medium | Manual Review | SQL Server running; aqtracker DB created; service account has db_owner permissions |  | No | Test pyodbc connection FIRST before proceeding to anything else
W1-D1-02 | Infrastructure | Database | Configure SQL Server TLS | Enable TLS encryption for all database connections (HIPAA: encryption in transit) | 1. Generate or install TLS certificate; 2. Configure SQL Server to require encrypted connections; 3. Test encrypted connection from Python | P0-Critical | W1-D1-01 |  | Medium | Manual Review | All connections use TLS; unencrypted connections are rejected | Yes | No | HIPAA requirement - encryption in transit
W1-D1-03 | Infrastructure | Database | Test pyodbc Connectivity | Verify Python can connect to SQL Server with pyodbc driver | 1. Install pyodbc and ODBC driver; 2. Write test connection script; 3. Verify read/write operations work; 4. Document connection string format | P0-Critical | W1-D1-01 |  | Medium | Vibe-Code | Python script connects; can CREATE TABLE and INSERT/SELECT; connection string documented | No | Yes | BLOCKER if this fails - entire backend depends on it. Have backup plan (pymssql)
W1-D1-04 | Infrastructure | Backend | FastAPI Project Scaffold | Create the FastAPI project folder structure and install all dependencies | 1. Create app/ app/api/ app/models/ app/schemas/ app/services/ app/core/ folders; 2. pip install fastapi uvicorn sqlalchemy pyodbc alembic python-jose passlib cryptography; 3. Create main.py with basic FastAPI app; 4. Create requirements.txt | P0-Critical | W1-D1-03 |  | Low | Vibe-Code | FastAPI app starts with uvicorn; all imports work; folder structure matches plan | No | No
W1-D1-05 | Infrastructure | Backend | Setup Alembic Migrations | Initialize Alembic for database migration management | 1. alembic init alembic; 2. Configure alembic.ini with SQL Server connection; 3. Update env.py to use SQLAlchemy metadata; 4. Test with empty migration | P1-High | W1-D1-04;W1-D1-03 |  | Low | Vibe-Code | alembic revision --autogenerate works; alembic upgrade head runs without error | No | No
W1-D1-06 | Infrastructure | Backend | SQLAlchemy Base Model | Create base SQLAlchemy model with audit columns (created_at updated_at created_by updated_by) | 1. Create app/models/base.py; 2. Define AuditMixin with created_at updated_at created_by updated_by; 3. Configure SQLAlchemy engine and session factory; 4. Create database dependency for FastAPI | P1-High | W1-D1-04 |  | Low | Vibe-Code | Base model works; audit columns auto-populate; session factory creates valid sessions | No | No
W1-D1-07 | Backend | Database | Schema Phase 1 - Users Table | Create users table with Keycloak integration fields | 1. Define User model (id email name role active keycloak_id); 2. Create Alembic migration; 3. Run migration | P1-High | W1-D1-05;W1-D1-06 |  | Low | Vibe-Code | users table exists in DB with correct columns and types | No | No
W1-D1-08 | Backend | Database | Schema Phase 1 - Reference Tables | Create clients facilities providers aprns tables | 1. Define Client model (id name active); 2. Define Facility model (id name client_id FK active); 3. Define Provider model (id name specialty active); 4. Define APRN model (id name provider_id FK active); 5. Create migration; 6. Run migration | P1-High | W1-D1-05;W1-D1-06 |  | Low | Vibe-Code | All 4 tables exist; foreign keys are correct; indexes on FKs created | No | No
W1-D1-09 | Backend | Database | Schema Phase 1 - Rounding Sheets Table | Create rounding_sheets table with all fields from prototype | 1. Define RoundingSheet model with ALL fields: id client_id facility_id provider_id user_id dos received_date batch_number total_encounters uploaded_count billed_count pending_count billing_date billed_by is_np_sheet is_handwritten remarks status ocr_fields(JSON); 2. Create migration; 3. Run migration | P0-Critical | W1-D1-05;W1-D1-06;W1-D1-08 |  | Low | Manual Review | Table matches prototype data structure exactly; JSON column works for ocr_fields; all FKs valid | No | No | Map EVERY field from roundingSheetsData.js to columns. Don't miss sourceImages ocrFields remarks
W1-D1-10 | Backend | Database | Schema Phase 1 - Encounters Table | Create encounters table with all coding and status fields | 1. Define Encounter model: id sheet_id(FK) patient_name dob mrn admission_date dos visit_type query billed_under_provider status cpt icd10(JSON) coder_id notes batch_number source_files(JSON); 2. Create migration; 3. Run migration | P0-Critical | W1-D1-05;W1-D1-06;W1-D1-09 |  | Low | Manual Review | Table exists; status enum values match prototype (missing draft ready submitted uploaded coded billed); JSON columns work | No | No
W1-D1-11 | Backend | Database | Schema Phase 1 - Patients Table | Create patients table with encrypted PHI fields | 1. Define Patient model: id name(encrypted) dob(encrypted) mrn(encrypted) created_at; 2. Plan encryption approach (Fernet at app level); 3. Create migration; 4. Run migration | P0-Critical | W1-D1-05;W1-D1-06 |  | High | Manual Review | Table exists; PHI columns are designed for encrypted storage; encryption will be implemented in Day 3 | Yes | No | PHI encryption implementation comes on Day 3 but schema must support it now
W1-D2-01 | Infrastructure | Auth | Install Keycloak | Install and configure Keycloak on deployment server | 1. Download and install Keycloak; 2. Start Keycloak service; 3. Access admin console; 4. Verify Keycloak is running on expected port | P0-Critical | None |  | Medium | Manual Review | Keycloak admin console accessible; can log in with admin credentials | No | No
W1-D2-02 | Infrastructure | Auth | Create Keycloak Realm & Clients | Configure aqtracker realm with FastAPI and React clients | 1. Create aqtracker realm; 2. Create confidential client for FastAPI (authorization code + client credentials); 3. Create public client for React SPA (PKCE flow); 4. Configure redirect URIs for both clients | P0-Critical | W1-D2-01 |  | High | Manual Review | Both clients configured; PKCE flow works for SPA client; client credentials flow works for FastAPI | Yes | No | PKCE flow is critical - if misconfigured auth will fail throughout the app
W1-D2-03 | Infrastructure | Auth | Create Keycloak Roles & Users | Set up RBAC roles and test user accounts | 1. Create roles: admin manager uploader coder biller; 2. Create test users (one per role); 3. Configure password policy (12 char min complexity 90-day rotation); 4. Assign roles to test users | P1-High | W1-D2-02 |  | Low | Manual Review | 5 roles exist; test users created and can log in; password policy enforced; role assignments correct | Yes | No
W1-D2-04 | Infrastructure | Auth | Keycloak Brute Force Protection | Configure account lockout for HIPAA compliance | 1. Enable brute force detection; 2. Set max login failures to 5; 3. Set lockout duration; 4. Test by failing 5 logins | P1-High | W1-D2-02 |  | Low | Manual Review | Account locks after 5 failed attempts; locked message shown to user | Yes | No | HIPAA requirement
W1-D2-05 | Backend | Auth | FastAPI JWT Validation Middleware | Build middleware to validate Keycloak-issued JWT tokens | 1. Create app/core/auth.py; 2. Fetch Keycloak public key / JWKS endpoint; 3. Validate token signature expiry issuer audience; 4. Extract user info and roles from token claims; 5. Create get_current_user dependency | P0-Critical | W1-D2-02;W1-D1-04 |  | High | Manual Review | Valid tokens accepted; expired tokens rejected 401; tampered tokens rejected; roles extracted correctly from claims | Yes | No | REVIEW EVERY LINE - auth bypass = PHI exposure
W1-D2-06 | Backend | Auth | Role-Based Dependencies | Build require_role and require_any_role FastAPI dependencies | 1. Create require_role(role_name) dependency; 2. Create require_any_role(*roles) dependency; 3. Test with different role tokens; 4. Return 403 for unauthorized roles | P0-Critical | W1-D2-05 |  | Medium | Manual Review | require_role('coder') rejects non-coder tokens with 403; require_any_role works with multiple roles | Yes | No
W1-D2-07 | Backend | Auth | CORS Configuration | Configure CORS for React frontend origin | 1. Add CORSMiddleware to FastAPI app; 2. Allow React dev server origin (localhost:5173); 3. Allow production origin; 4. Configure allowed methods and headers | P1-High | W1-D1-04 |  | Low | Vibe-Code | React frontend can make API calls without CORS errors; preflight requests succeed | No | No
W1-D2-08 | Backend | Database | Schema Phase 2 - Billing Records | Create billing_records table | 1. Define BillingRecord model: id encounter_id(FK) dos visit_type provider patient mrn dob coder cpt icd10 icd10_full charge_amount facility aprn admission_date batch_number status comment; 2. Create and run migration | P1-High | W1-D1-05;W1-D1-06 |  | Low | Vibe-Code | Table exists with correct columns; FK to encounters works | No | No
W1-D2-09 | Backend | Database | Schema Phase 2 - Queries & Flagged Queries | Create queries and flagged_queries tables | 1. Define Query model: id source facility dos visit_type provider patient uploader coder biller assigned_to status flagged_at flagged_by; 2. Define FlaggedQuery model: id record_id source_module reason flagged_by flagged_at; 3. Create and run migrations | P1-High | W1-D1-05;W1-D1-06 |  | Low | Vibe-Code | Both tables exist; source enum matches prototype (Upload Coding Billing) | No | No
W1-D2-10 | Backend | Database | Schema Phase 2 - Activity Log | Create activity_log table | 1. Define ActivityLog model: id timestamp user_id user_name action module summary details(JSON) ip_address; 2. Module enum: ROUNDING_SHEET UPLOAD CODING BILLING QUERIES HISTORY SESSION; 3. Create and run migration | P1-High | W1-D1-05;W1-D1-06 |  | Low | Vibe-Code | Table exists; JSON details column works; module enum matches prototype | No | No
W1-D2-11 | Backend | Database | Schema Phase 2 - Document Files | Create document_files table | 1. Define DocumentFile model: id sheet_id encounter_id filename file_path(will be encrypted) file_type file_size uploaded_by uploaded_at; 2. Create and run migration | P1-High | W1-D1-05;W1-D1-06 |  | Low | Vibe-Code | Table exists; FKs to sheets and encounters work; file_type supports pdf jpg jpeg png | No | No
W1-D2-12 | Backend | Database | Schema Phase 2 - Coding Sessions | Create coding_sessions table for AI audit trail | 1. Define CodingSession model: id encounter_id coder_id ai_suggestions(JSON) applied_codes(JSON) raf_score hcc_count started_at completed_at; 2. Create and run migration | P1-High | W1-D1-05;W1-D1-06 |  | Low | Vibe-Code | Table exists; JSON columns store AI vs coder selections for audit | Yes | No | Critical for auditing what AI suggested vs what coder accepted
W1-D2-13 | Backend | Database | Schema Phase 2 - Audit Trail (Immutable) | Create audit_trail table with immutability trigger | 1. Define AuditTrail model: id timestamp user_id action(CRUD) table_name record_id ip_address old_values(JSON) new_values(JSON); 2. Create migration; 3. Create SQL Server trigger to prevent UPDATE/DELETE on this table; 4. Test trigger blocks modifications | P0-Critical | W1-D1-05;W1-D1-06 |  | High | Manual Review | Table exists; INSERT works; UPDATE fails with error; DELETE fails with error; trigger is active | Yes | Yes | HIPAA-critical: immutable audit trail. Verify trigger works by attempting UPDATE and DELETE
W1-D3-01 | Backend | HIPAA | Configure SQL Server TDE | Enable Transparent Data Encryption for encryption at rest | 1. Create database master key; 2. Create certificate for TDE; 3. Create database encryption key; 4. Enable encryption on aqtracker database; 5. Verify encryption state | P0-Critical | W1-D1-01 |  | High | Manual Review | sys.dm_database_encryption_keys shows encryption_state = 3 (encrypted); backup cert stored securely | Yes | No | HIPAA requirement - encryption at rest
W1-D3-02 | Backend | HIPAA | Build PHI Encryption Utility | Create Fernet-based encrypt/decrypt functions for PHI fields | 1. Create app/core/security.py; 2. Load encryption key from ENCRYPTION_KEY env var; 3. Build encrypt_phi(plaintext) -> ciphertext function; 4. Build decrypt_phi(ciphertext) -> plaintext function; 5. Build key rotation support (store key version); 6. Test roundtrip: encrypt -> decrypt = original | P0-Critical | W1-D1-04 |  | High | Manual Review | encrypt/decrypt roundtrip works; key loaded from env var only; error on missing key; ciphertext is not readable | Yes | No | REVIEW EVERY LINE. Key must NEVER be in code. Test by checking raw DB values are ciphertext.
W1-D3-03 | Backend | HIPAA | Build Audit Logging Middleware | Create FastAPI middleware that logs every API call | 1. Create audit middleware in app/core/audit.py; 2. Log: user_id endpoint method ip_address timestamp; 3. For PHI-touching endpoints: log table_name record_id action; 4. For UPDATEs: capture old_values and new_values; 5. Write to audit_trail table | P0-Critical | W1-D2-13;W1-D2-05 |  | High | Manual Review | Every API call creates an audit entry; PHI reads are logged; old/new values captured on updates | Yes | No | REVIEW EVERY LINE. This is the HIPAA compliance backbone. No endpoint can skip logging.
W1-D3-04 | Backend | Rounding Sheets | Rounding Sheets - List API | GET /api/rounding-sheets with filters pagination search | 1. Create app/api/rounding_sheets.py router; 2. Build list endpoint with query params: status client_id search page page_size; 3. Include status counts (draft/verified/manual) in response; 4. Sort by DOS descending; 5. Add require_role dependency | P1-High | W1-D1-09;W1-D2-05 |  | Low | Vibe-Code | List returns paginated results; status filter works; search across columns works; status counts correct | No | No
W1-D3-05 | Backend | Rounding Sheets | Rounding Sheets - Create API | POST /api/rounding-sheets | 1. Build create endpoint; 2. Accept all form fields; 3. Validate required fields (total_encounters > 0); 4. Set initial status to Draft; 5. Log activity (module: ROUNDING_SHEET action: Created); 6. Return created sheet | P1-High | W1-D3-04;W1-D2-10 |  | Low | Vibe-Code | Sheet created in DB; activity logged; validation errors return 422; status defaults to Draft | No | No
W1-D3-06 | Backend | Rounding Sheets | Rounding Sheets - Detail Update Verify APIs | GET PUT PATCH endpoints for single rounding sheet | 1. GET /api/rounding-sheets/{id} - return full detail; 2. PUT /api/rounding-sheets/{id} - update all fields; 3. PATCH /api/rounding-sheets/{id}/verify - mark as verified; 4. Log all changes to activity log | P1-High | W1-D3-04 |  | Low | Vibe-Code | Detail returns all fields; update persists; verify changes status; 404 for missing IDs; activity logged | No | No
W1-D3-07 | Backend | Documents | Document Upload API | POST /api/documents/upload for file uploads | 1. Create app/api/documents.py router; 2. Accept multipart file upload; 3. Validate file type (pdf jpg jpeg png); 4. Generate UUID-based filename; 5. Store in /{year}/{month}/{sheet_id}/ directory; 6. Encrypt file at rest (AES-256); 7. Save metadata to document_files table | P1-High | W1-D2-11;W1-D3-02 |  | Medium | Manual Review | Files upload successfully; stored with UUID names; encrypted on disk; metadata in DB; file type validated | Yes | No | File paths must use UUIDs not sequential IDs (security). Files encrypted at rest.
W1-D3-08 | Backend | Documents | Document Retrieval API | GET /api/documents/{id} for streaming file downloads | 1. GET endpoint streams file content; 2. Decrypt file before streaming; 3. Set correct Content-Type header; 4. Require authentication; 5. Log document access in audit trail | P1-High | W1-D3-07 |  | Medium | Manual Review | Files stream correctly; PDFs render in browser; images display; unauthorized access returns 401; access logged | Yes | No | Every document access must be audit-logged (HIPAA)
W1-D3-09 | Backend | Documents | Thumbnail Generation Service | Generate image thumbnails for the document viewer | 1. Create thumbnail service in app/services/thumbnail_service.py; 2. On image upload: generate 52x68px thumbnail; 3. Store thumbnail alongside original; 4. Return thumbnail URL in document metadata | P2-Medium | W1-D3-07 |  | Low | Vibe-Code | Thumbnails generated for images; correct aspect ratio; accessible via API | No | No
W1-D4-01 | Backend | Encounters | Encounters - List API | GET /api/rounding-sheets/{id}/encounters | 1. Create app/api/encounters.py router; 2. List all encounters for a sheet; 3. Include status calculation (missing/draft/ready/submitted) based on field completeness; 4. Return status counts for summary bar | P1-High | W1-D1-10;W1-D3-04 |  | Low | Vibe-Code | Returns encounters with correct status; missing = all empty; draft = partial; ready = all required filled | No | No
W1-D4-02 | Backend | Encounters | Encounters - Update & Bulk Update | PUT single and POST bulk-update endpoints | 1. PUT /api/encounters/{id} - update single encounter field; 2. POST /api/encounters/bulk-update - save all encounters; 3. Recalculate status after each update; 4. Log field changes to activity log | P1-High | W1-D4-01 |  | Low | Vibe-Code | Single update works; bulk update saves all encounters; status recalculated; changes logged | No | No
W1-D4-03 | Backend | Encounters | Encounters - BUP & Query Toggles | PATCH endpoints for BUP and query flag toggles | 1. PATCH /api/encounters/{id}/bup - toggle billed_under_provider; 2. PATCH /api/encounters/{id}/query - toggle query flag; 3. BUP only allowed for APRN sheets (validate); 4. Log toggles to activity log | P1-High | W1-D4-01 |  | Medium | Manual Review | BUP toggle works; rejects non-APRN sheets; query toggle works; both logged | No | No | BUP business rule: only available on APRN rounding sheets
W1-D4-04 | Backend | Patients | Patient Lookup API | GET /api/patients/lookup with name and DOB search | 1. Create app/api/patients.py router; 2. Search by patient name and DOB (decrypt PHI for comparison); 3. Return patient with visit history; 4. Include visit details: dos admission_date provider facility visit_type status | P1-High | W1-D1-11;W1-D3-02 |  | Medium | Manual Review | Lookup finds matching patients; returns visit history; handles encrypted PHI correctly; no match returns null | Yes | No | PHI is encrypted in DB - lookup must decrypt for comparison. Review encryption handling.
W1-D4-05 | Backend | Patients | Duplicate Detection Logic | Detect potential duplicate encounters across providers | 1. Match on: patient name + DOB + admission date + DOS; 2. Flag when same patient same dates but different provider; 3. Return duplicate risk info in lookup response; 4. Include matching record details for comparison | P0-Critical | W1-D4-04 |  | High | Manual Review | Duplicates detected correctly; different-provider matches flagged; same-provider not flagged; edge cases handled | No | No | CORE BUSINESS RULE. Review SQL query carefully. Test with edge cases: same name different DOB etc.
W1-D4-06 | Frontend | Auth | Install keycloak-js | Add Keycloak JavaScript adapter to React app | 1. npm install keycloak-js; 2. Create src/services/auth.js; 3. Initialize Keycloak with realm and client config; 4. Configure PKCE flow | P0-Critical | W1-D2-02 |  | Medium | Manual Review | keycloak-js installed; Keycloak initializes; PKCE flow configured with correct client ID | No | No
W1-D4-07 | Frontend | Auth | Replace Login with Keycloak Redirect | Remove mock LoginForm; use Keycloak redirect flow | 1. Remove LoginForm container and component; 2. Wrap App with Keycloak auth check; 3. Redirect to Keycloak login if not authenticated; 4. Handle login callback; 5. Store token in memory (not localStorage) | P0-Critical | W1-D4-06 |  | High | Manual Review | Unauthenticated users redirected to Keycloak; login returns to app; token available for API calls | Yes | No | Token must NOT be stored in localStorage (XSS risk). Use keycloak-js built-in token management.
W1-D4-08 | Frontend | Auth | Setup Axios Auth Interceptor | Attach Bearer token to all API requests | 1. Create src/services/api.js with Axios instance; 2. Add request interceptor to attach Authorization: Bearer {token}; 3. Add response interceptor: 401 -> redirect to Keycloak login; 4. Add 500 -> show error toast; 5. Configure base URL | P0-Critical | W1-D4-07 |  | Medium | Manual Review | All API calls include Bearer token; 401 responses redirect to login; error toasts shown for server errors | No | No
W1-D4-09 | Frontend | Auth | Update TopBar with Real User | Show real username from Keycloak token; wire sign-out | 1. Update TopBar.jsx to read username from Keycloak token claims; 2. Wire sign-out button to Keycloak logout; 3. Clear all state on logout; 4. Protect all routes with auth check | P1-High | W1-D4-07 |  | Low | Vibe-Code | TopBar shows real username; sign-out redirects to Keycloak logout; all routes protected | No | No
W1-D5-01 | Backend | Upload | Upload - Sheet List API | GET /api/uploads/sheets for available rounding sheets | 1. Create app/api/uploads.py router; 2. Return sheets available for upload with: provider DOS batch facility encounter count; 3. Include upload progress (submitted vs total); 4. Filter by status | P1-High | W1-D3-04 |  | Low | Vibe-Code | Returns sheets with metadata matching prototype selector format | No | No
W1-D5-02 | Backend | Upload | Upload - Submit Encounter API | POST /api/uploads/submit for individual encounter submission | 1. Accept encounter_id; 2. Validate all required fields filled; 3. Mark encounter status as Uploaded; 4. Route to coding queue; 5. Log submission to activity log with full details | P1-High | W1-D5-01;W1-D4-01 |  | Medium | Manual Review | Submission changes status; validates completeness; logged; encounter appears in coding queue | No | No | Review status transition logic - submitted encounters must appear in Coding module
W1-D5-03 | Backend | Upload | Upload - Encounter Attachments | Handle per-encounter file attachments in upload flow | 1. POST /api/encounters/{id}/attachments - attach files to encounter; 2. Link document_files to encounter_id; 3. Return attachment list with encounter data | P2-Medium | W1-D3-07;W1-D4-01 |  | Low | Vibe-Code | Files attach to encounters; appear in encounter response; accessible via document API | No | No
W1-D5-04 | Backend | Coding | Coding - Patient List API | GET /api/coding/patients with pending/coded counts | 1. Create app/api/coding.py router; 2. Return patients with: pending count coded count total visits; 3. Sort by pending (descending); 4. Include filters: client facility search show_assigned_to_others; 5. Pagination | P1-High | W1-D1-10;W1-D2-05 |  | Low | Vibe-Code | Patient list returns correct pending/coded counts; sorted by most pending first; filters work | No | No
W1-D5-05 | Backend | Coding | Coding - Stats & Productivity APIs | GET /api/coding/stats and /api/coding/productivity | 1. Stats: total_visits total_coded completion_percentage; 2. Productivity: coded_today coded_this_week avg_per_day prev_week_avg trend(up/down) delta estimated_completion_days; 3. Calculate from coding_sessions table | P1-High | W1-D5-04;W1-D2-12 |  | Medium | Manual Review | Stats match real data; trend calculation correct (compare current week avg vs previous); estimated days correct | No | No | Review calculation logic - these metrics are visible on the main coding page
W1-D5-06 | Backend | Coding | Coding - Take/Claim Encounter API | POST /api/coding/encounters/{id}/take | 1. Claim encounter for current user; 2. Set coder_id on encounter; 3. Implement optimistic concurrency (version column or row lock); 4. Reject if already claimed by another user; 5. Log claim to activity log | P0-Critical | W1-D5-04 |  | High | Manual Review | Claim succeeds for unclaimed encounters; fails for already-claimed; concurrent claims don't both succeed | No | No | REVIEW: Must prevent two coders claiming same encounter. Use version column or SELECT FOR UPDATE.
W1-D5-07 | Backend | Coding | Coding - Apply Codes API | POST /api/coding/encounters/{id}/apply | 1. Accept: cpt icd10_codes(with priority order) notes query_text raf_score hcc_count; 2. Update encounter with applied codes; 3. Mark encounter status as Coded; 4. Log to activity log | P1-High | W1-D5-04 |  | Low | Vibe-Code | Codes saved; status changes to Coded; ICD-10 priority order preserved; activity logged | No | No
W1-D5-08 | Backend | Coding | Coding - H&P Code Inheritance API | GET /api/coding/encounters/{id}/carried-codes | 1. Find patient's most recent H&P visit before current encounter date; 2. Return ICD-10 codes from that H&P visit as carried-over suggestions; 3. Include source info (H&P DOS and provider); 4. Return empty if no prior H&P found | P1-High | W1-D5-04;W1-D4-04 |  | Medium | Manual Review | Finds correct prior H&P; returns its ICD-10 codes; date comparison is correct; no H&P returns empty array | No | No | Business rule: only inherit from H&P visits not Follow Up or Initial. Date must be BEFORE current encounter.
W1-D5-09 | Backend | Coding | Coding - Encounter List API | GET /api/coding/patients/{id}/encounters | 1. Return all encounters for a patient; 2. Include: batch dos admission_date visit_type provider coder cpt icd10 status source_files; 3. Sort: Uploaded/Applied first then Billed; 4. Only Uploaded/Applied are clickable | P1-High | W1-D5-04 |  | Low | Vibe-Code | Returns encounters with correct status sorting; source files referenced for document viewer | No | No
W1-D6-01 | Backend | Billing | Billing - List API | GET /api/billing with filters and pagination | 1. Create app/api/billing.py router; 2. Query params: client_id facility_id search page page_size; 3. Search across: patient mrn provider cpt icd10; 4. Return charge_amount formatted as currency; 5. ICD10 truncated at 16 chars in list | P1-High | W1-D2-08;W1-D2-05 |  | Low | Vibe-Code | List returns paginated results; search works across multiple fields; charge amounts formatted | No | No
W1-D6-02 | Backend | Billing | Billing - Detail & Edit APIs | GET PUT PATCH endpoints for billing records | 1. GET /api/billing/{id} - full detail with all sections; 2. PUT /api/billing/{id} - edit all fields; 3. PATCH /api/billing/{id}/status - set Billed or Query + comment (max 500 chars); 4. PATCH /api/billing/{id}/release - unlock; 5. Validate status selection is required | P1-High | W1-D6-01 |  | Medium | Manual Review | Detail returns all fields; edit persists; status validation works (empty status returns error); release works | No | No | Status validation: must select Billed or Query before save. Match prototype's validation behavior exactly.
W1-D6-03 | Backend | Billing | Billing - Query Flag APIs | POST DELETE for flagging/unflagging billing queries | 1. POST /api/billing/{id}/flag - create flagged_query record with source metadata; 2. DELETE /api/billing/{id}/flag - remove query flag; 3. Log both actions to activity log; 4. Return flagged status with billing list | P1-High | W1-D6-01;W1-D2-09 |  | Low | Vibe-Code | Flag creates record in flagged_queries; unflag removes it; flagged IDs returned with list; activity logged | No | No
W1-D6-04 | Backend | Queries | Queries - List API | GET /api/queries with filters | 1. Create app/api/queries.py router; 2. List with: my_queries_only search pagination; 3. My-queries filter: only show queries flagged by current user; 4. Search across all columns | P1-High | W1-D2-09;W1-D2-05 |  | Low | Vibe-Code | Returns queries; my-queries filter works; search works; pagination works | No | No
W1-D6-05 | Backend | Queries | Queries - APRN APIs | GET /api/queries/aprn list and detail | 1. GET /api/queries/aprn - NP/APRN queries list; 2. GET /api/queries/aprn/{id} - detail with source document references (rounding sheet + progress note files); 3. Include: mrn dob patient admission_date visit_type aprn source_files | P1-High | W1-D6-04 |  | Low | Vibe-Code | APRN list returns correct data; detail includes source file references for document viewer | No | No
W1-D6-06 | Backend | Queries | Queries - CSV Export | POST /api/queries/export | 1. Generate CSV from filtered query data; 2. Return as downloadable file; 3. Log export to activity log with module row_count filter_criteria | P2-Medium | W1-D6-04 |  | Low | Vibe-Code | CSV downloads; columns match table; export logged with row count | No | No
W1-D6-07 | Backend | History | History - List API | GET /api/history with all filters | 1. Create app/api/history.py router; 2. Filters: client_id(cascading facility) facility_id date_from date_to show_all search page page_size; 3. Return 13 columns + detail data for expandable rows; 4. Facility list changes based on selected client; 5. Pagination: 10/25/50/100 options | P1-High | W1-D2-08;W1-D2-05 |  | Medium | Vibe-Code | All filters work; client cascades facility options; date range works; search across all columns; 4000+ rows paginate efficiently | No | No | Large dataset - add indexes on commonly filtered columns
W1-D6-08 | Backend | History | History - CSV Export | POST /api/history/export | 1. Generate CSV from filtered history data; 2. Handle large datasets (4000+ rows); 3. Stream response for large files; 4. Log export to activity log | P2-Medium | W1-D6-07 |  | Low | Vibe-Code | CSV downloads even for large datasets; streaming works; export logged | No | No
W1-D6-09 | Backend | Activity Log | Activity Log - List API | GET /api/activity-log with filters | 1. Create app/api/activity_log.py router; 2. Filters: module(enum) date_from date_to search page page_size; 3. Return entries newest-first; 4. Include expandable details for entries with additional data; 5. Module badges with colors | P1-High | W1-D2-10;W1-D2-05 |  | Low | Vibe-Code | Returns activity entries; module filter works; date range works; search works; details included | No | No
W1-D6-10 | Backend | Activity Log | Activity Log Service | Build log_activity() service used throughout the app | 1. Create app/services/activity_service.py; 2. Function: log_activity(action module summary details user); 3. Auto-populate timestamp; 4. Store in activity_log table; 5. Export as reusable service for all modules | P1-High | W1-D2-10 |  | Low | Vibe-Code | log_activity callable from any service; entries appear in activity log; timestamp auto-set | No | No
W1-D7-01 | Backend | Dashboard | Dashboard - Stats API | GET /api/dashboard/stats | 1. Create app/api/dashboard.py router; 2. Today stats: COUNT encounters uploaded/coded/billed today; 3. All-time stats: COUNT pending coding pending billing open queries; 4. Single query or cached computation | P1-High | W1-D1-10;W1-D2-08;W1-D2-09 |  | Low | Vibe-Code | Stats return correct counts from real database; today's date boundary correct | No | No
W1-D7-02 | Backend | Dashboard | Dashboard - Volume Chart API | GET /api/dashboard/volume?days=7 | 1. Return daily encounter counts for last N days; 2. Three series: uploaded coded billed per day; 3. Labels: day names from date range; 4. Return as arrays matching frontend chart format | P1-High | W1-D7-01 |  | Low | Vibe-Code | Returns 7 days of data; three series align with correct dates; format matches frontend BarChart expectations | No | No
W1-D7-03 | Frontend | Shared | Create API Service Layer | Build Axios instance and per-module service files | 1. Create src/services/api.js (Axios instance + auth interceptor); 2. Create 10 service files: roundingSheetService encounterService uploadService codingService billingService queryService historyService activityLogService dashboardService documentService; 3. Each file wraps corresponding API endpoints | P1-High | W1-D4-08 |  | Low | Vibe-Code | All service files created; each function matches API endpoint; error handling consistent | No | No | Give this to Agent Terminal 2 - repetitive but important. One function per endpoint.
W1-D7-04 | Frontend | Rounding Sheets | Migrate RoundingSheetV2 Container | Replace useLocalStorage with API calls | 1. Replace useLocalStorage('rounding-sheet-rows') with useState + useEffect; 2. Fetch list on mount via roundingSheetService.getList(); 3. Filter/search via API query params; 4. Create dialog POSTs to API; 5. Status filter as query param; 6. Add loading state while fetching; 7. Remove all localStorage imports | P0-Critical | W1-D7-03;W1-D3-04 |  | Medium | Both | Page loads data from API; create saves to API; filters work via API; no localStorage usage; loading skeleton shows during fetch | No | Yes | FIRST FRONTEND MIGRATION. Go slow and get the pattern right - all other migrations follow this pattern.
W1-D7-05 | Frontend | Dashboard | Migrate Dashboard Container | Replace static imports with API calls | 1. Replace todayStats/allTimeStats/encounterVolumeData imports with API calls; 2. Fetch from dashboardService on mount; 3. Add loading skeleton; 4. Chart renders with real data | P1-High | W1-D7-03;W1-D7-01 |  | Low | Vibe-Code | Dashboard shows real stats; chart renders real volume data; loading skeleton during fetch | No | No
W2-D8-01 | Frontend | Rounding Sheets | Migrate RoundingSheetDetailV2 | Wire 2-step wizard to API | 1. Load sheet data from GET /api/rounding-sheets/{id}; 2. Step 1 form saves via PUT; 3. Step 2 encounters load from GET; 4. Inline edits PATCH individual encounters; 5. BUP toggle calls API; 6. File attachments upload/display via document API; 7. Save confirmation dialog uses API data for handwritten/NP detection; 8. Stepper full-screen splitter remain UI-only | P0-Critical | W1-D7-04;W1-D4-01;W1-D3-07 |  | Medium | Both | Full wizard flow works: load -> edit Step 1 -> save -> view Step 2 encounters -> edit inline -> save; document viewer shows real files | No | No | Most complex migration after EncountersV2. Test every interaction.
W2-D8-02 | Frontend | Upload | Migrate UploadV2 Container | Wire upload page to API | 1. Sheet selector fetches from uploadService.getSheets(); 2. Encounter table loads from API per sheet; 3. Field edits PATCH encounters; 4. Patient history lookup via patientService; 5. Duplicate detection from API response; 6. Submit calls uploadService.submit() | P0-Critical | W1-D7-03;W1-D5-01;W1-D4-04 |  | Medium | Both | Sheet selection loads encounters; field edits persist; patient lookup works; duplicate detection fires; submit changes status | No | No
W2-D8-03 | Frontend | Upload | Upload Migration - Documents & BUP | Wire document viewer BUP and redirect | 1. Document viewer loads files from documentService; 2. BUP confirmation triggers API PATCH; 3. Duplicate comparison dialog loads existing record from API; 4. Redirect after submit navigates to Coding with real IDs; 5. Per-encounter attachment upload via API | P1-High | W2-D8-02;W1-D3-07 |  | Low | Vibe-Code | Documents display from API; BUP saves; duplicate comparison shows real data; redirect to coding works | No | No
W2-D9-01 | Frontend | Coding | Migrate CodingV2 Container | Wire coding patient list to API | 1. Patient list from codingService.getPatients(); 2. Stats strip from codingService.getStats(); 3. Productivity strip from codingService.getProductivity(); 4. Filters as query params; 5. Encounter table from codingService.getEncounters(); 6. TAKE button calls codingService.take(); 7. Carried codes from codingService.getCarriedCodes() | P1-High | W1-D7-03;W1-D5-04 |  | Medium | Both | Patient list shows real data; stats correct; productivity metrics display; TAKE claims encounter; carried codes load | No | No
W2-D9-02 | Frontend | Coding | Migrate EncountersV2 Workspace | Wire 5-state workspace to API (most complex) | 1. Encounter selection loads data from API; 2. Form state populated from API data; 3. Analyze button calls /api/coding/encounters/{id}/analyze (mock response for now until Day 13); 4. Results display from API response; 5. Sequential review (4 sections) remains UI state; 6. Apply calls /api/coding/encounters/{id}/apply; 7. Document viewer loads from document API | P0-Critical | W2-D9-01;W1-D5-07 |  | High | Both | Full workspace state machine works: Form -> Analyzing -> Results -> Summary -> Applied; all transitions work; data persists | No | No | MOST COMPLEX CONTAINER. 25+ state fields. Test every state transition. Use mock analyze response until Day 13.
W2-D9-03 | Frontend | Billing | Migrate BillingV2 + BillingDetailV2 | Wire billing list and detail to API | 1. Billing list from billingService.getList(); 2. Filters and loading skeleton; 3. Detail from billingService.getDetail(); 4. Edit mode PUTs; 5. Status save PATCHes; 6. Release PATCHes; 7. Query flag/unflag; 8. Toast notifications | P1-High | W1-D7-03;W1-D6-01 |  | Low | Vibe-Code | List loads with filters; detail shows all sections; edit saves; status validates; release works; toasts show | No | No
W2-D10-01 | Frontend | Queries | Migrate Queries Container | Wire both tabs to API | 1. Queries tab from queryService.getList(); 2. My-queries filter as param; 3. NP/APRN tab from queryService.getAprn(); 4. Detail view with document loading; 5. Export CSV triggers download; 6. Empty states | P1-High | W1-D7-03;W1-D6-04 |  | Low | Vibe-Code | Both tabs load; my-queries filter works; APRN detail shows documents; export downloads CSV | No | No
W2-D10-02 | Frontend | History | Migrate History Container | Wire history table with all filters to API | 1. All filters via API query params; 2. Client cascading facility (facility options change when client changes); 3. Date range and All toggle; 4. Row selection + expandable detail panel; 5. CSV export; 6. Pagination 10/25/50/100 | P1-High | W1-D7-03;W1-D6-07 |  | Low | Vibe-Code | All filters work; cascading facility works; row expansion shows detail; export works; pagination handles 4000+ rows | No | No
W2-D10-03 | Frontend | Activity Log | Migrate Activity Log Container | Wire activity log to API | 1. Module filter date range search via API; 2. Expandable row details; 3. CSV export; 4. Entry count display; 5. Refresh button | P1-High | W1-D7-03;W1-D6-09 |  | Low | Vibe-Code | All filters work; expandable details show; export works; count accurate | No | No
W2-D10-04 | Frontend | Auth | Keycloak Final Polish | Handle token expiry silent refresh and global error boundary | 1. Implement silent token refresh before expiry; 2. If refresh fails redirect to Keycloak login; 3. Global error boundary: 401 -> redirect; 4. Logout clears all state; 5. Session expired message | P0-Critical | W1-D4-07 |  | Medium | Manual Review | Token refreshes silently; expired session redirects to login; logout clears everything; no stale tokens | Yes | No
W2-D10-05 | Frontend | Shared | Remove All localStorage Usage | Delete all useLocalStorage imports and mock data imports | 1. Search for every useLocalStorage import; 2. Remove all localStorage keys; 3. Remove mock data imports from containers; 4. Verify no container references localStorage; 5. Keep useLocalStorage hook file for reference only | P0-Critical | W2-D10-01;W2-D10-02;W2-D10-03;W2-D9-03 |  | Low | Vibe-Code | Zero localStorage usage in containers; all data from API; app fully functional against backend | No | Yes | MILESTONE: All prototype features now running against real backend. Test every page.
W2-D11-01 | Infrastructure | OCR | Install Tesseract | Install Tesseract OCR engine and Python dependencies | 1. Install Tesseract on deployment server; 2. pip install pytesseract Pillow opencv-python pdf2image; 3. Install poppler for PDF conversion; 4. Verify tesseract CLI works; 5. Verify pytesseract can call it from Python | P0-Critical | None |  | Medium | Manual Review | tesseract --version works; pytesseract.image_to_string() returns text from test image | No | No
W2-D11-02 | Backend | OCR | OCR Preprocessing Pipeline | Build image preprocessing for better OCR accuracy | 1. Create app/services/ocr_service.py; 2. Image deskew (correct rotation using OpenCV); 3. Noise removal (bilateral filter); 4. Binarization (adaptive thresholding); 5. PDF to images conversion (pdf2image); 6. Build extract_text(image_path) base function | P1-High | W2-D11-01 |  | Medium | Both | Preprocessing improves OCR accuracy; skewed images are straightened; noise removed; PDFs converted to images | No | No
W2-D11-03 | Backend | OCR | Zone-Based Field Extraction | Define template zones and extract structured data | 1. Define zone config: { field_name: {x y width height} } for each rounding sheet field; 2. Crop each region from image; 3. OCR each region individually; 4. Clean results (strip whitespace normalize dates); 5. Calculate per-field confidence (Tesseract word-level scores); 6. Map confidence: >85% high 60-85% medium <60% low; 7. Output: { field: {value confidence confidence_level} } | P0-Critical | W2-D11-02 |  | High | Manual Review | Fields extracted correctly from real sample rounding sheets; confidence levels reasonable; zone coordinates accurate | No | No | TEST WITH REAL SAMPLES. This is the moment of truth for OCR. If zone-based fails consider full-page + regex.
W2-D11-04 | Backend | OCR | OCR API Endpoints | POST /api/ocr/process and GET /api/ocr/status | 1. POST /api/ocr/process - accepts document_id runs extraction as BackgroundTask; 2. Store results in rounding_sheets.ocr_fields JSON; 3. GET /api/ocr/status/{task_id} - check processing status; 4. Wire into rounding sheet creation: upload -> OCR -> pre-fill | P1-High | W2-D11-03;W1-D3-07 |  | Medium | Both | OCR runs async; status endpoint works; results stored in DB; form pre-fills with extracted data on detail page load | No | Yes | CHECKPOINT: Test full flow: upload document -> OCR extracts -> form shows pre-filled values with confidence indicators
W2-D12-01 | Backend | OCR | Handwritten Detection | Build classifier to detect handwritten vs printed sheets | 1. Analyze stroke density and connected components; 2. Compare OEM mode results (typed vs handwritten); 3. For handwritten: use --oem 1 (LSTM) --psm 6; 4. Lower confidence thresholds for handwritten; 5. Flag sheet is_handwritten=true; 6. Store detection result in DB | P1-High | W2-D11-03 |  | High | Manual Review | Handwritten sheets detected correctly; LSTM mode used; lower thresholds applied; flag stored in DB | No | No | If handwritten detection is unreliable consider adding a manual toggle in the UI
W2-D12-02 | Frontend | OCR | OCR Confidence UI Flow | Wire real OCR confidence to frontend indicators | 1. Load ocr_fields from rounding sheet API response; 2. Display per-field confidence borders (green/orange/red); 3. OCR legend panel shows real counts per level; 4. Pre-fill form fields from OCR data; 5. Handwritten flag shows red pen icon | P1-High | W2-D11-04;W2-D8-01 |  | Low | Vibe-Code | Confidence indicators show real values; legend counts correct; form pre-filled; pen icon for handwritten | No | No
W2-D12-03 | Backend | OCR | Encounter Generation from OCR | Extract table rows from OCR to create encounters | 1. Parse multi-patient rounding sheet table rows; 2. Each row becomes an encounter record; 3. Status based on extraction: missing (empty) draft (partial) ready (complete); 4. Replace mock generateEncountersForSheet(); 5. Test full flow: upload -> OCR -> encounters in Step 2 | P0-Critical | W2-D11-03;W1-D4-01 |  | High | Manual Review | Encounters generated from OCR; status reflects extraction quality; Step 2 table shows real extracted data | No | Yes | CHECKPOINT: Complete OCR pipeline working end-to-end. Upload document -> OCR -> encounters appear.
W2-D13-01 | Backend | AI | AQ Coder API Bridge | Build HTTP client to call existing AQ Coder service | 1. Create app/services/aqcoder_service.py; 2. Build async HTTP client; 3. Map AQ Coder response to frontend format: cptSuggestions[] icdCodes[] rafScore{} hccCount alerts[] mdmSummary{} mipsQuality[] supplementalCpt[]; 4. Handle timeouts (30s) errors retries (max 2) | P0-Critical | W1-D1-04 |  | High | Manual Review | Client calls AQ Coder; response mapped correctly to frontend format; timeouts handled; retries work; errors don't crash | No | No | REVIEW response mapping carefully. If shapes don't match the 4-section results screen breaks entirely.
W2-D13-02 | Backend | AI | Wire AQ Coder to Analyze Endpoint | POST /api/coding/encounters/{id}/analyze | 1. Send encounter data to AQ Coder: patient info visit_type clinical_notes existing_codes carried_codes; 2. Transform response to frontend format; 3. Return structured results for 4-section review; 4. Progress stages as real processing or UX polish | P0-Critical | W2-D13-01;W1-D5-04 |  | High | Manual Review | Analyze endpoint returns real AI results; frontend displays in Results screen; all 4 sections populate correctly | No | No
W2-D13-03 | Backend | AI | Coding Session Persistence | Store AI suggestions vs coder selections for audit | 1. On analyze: store AI raw suggestions in coding_sessions.ai_suggestions; 2. On apply: store final selections in coding_sessions.applied_codes; 3. Calculate diff: what was accepted rejected modified; 4. Log analysis + apply to activity log; 5. Update encounter status to Coded | P1-High | W2-D13-02;W1-D2-12 |  | Medium | Manual Review | Coding sessions stored; AI vs coder diff trackable; activity logged; encounter status changes to Coded | Yes | No | AUDIT-CRITICAL: Must track what AI suggested vs what coder accepted. Required for compliance.
W2-D14-01 | Infrastructure | Email | Azure AD App Registration | Register app in Entra ID for Outlook access | 1. Register application in Azure AD; 2. Configure Mail.Read Mail.ReadWrite permissions; 3. Set up client credentials flow; 4. Get admin consent; 5. Store client_id client_secret tenant_id in env vars; 6. Test: can read target mailbox | P0-Critical | None | Admin consent may require IT team approval | High | Manual Review | App registered; admin consent granted; can authenticate and list inbox messages via Graph API | No | No | START THIS EARLY if admin consent requires approval. May block Day 14 otherwise.
W2-D14-02 | Backend | Email | Email Service Client | Build Microsoft Graph API client | 1. Create app/services/email_service.py; 2. OAuth2 client credentials authentication; 3. Token caching and auto-refresh; 4. List messages endpoint; 5. Download attachment endpoint; 6. Mark as read endpoint | P1-High | W2-D14-01 |  | Medium | Manual Review | Client authenticates; can list messages; can download attachments; token refreshes automatically | No | No | Credentials must be in env vars. Tokens in memory only. Error messages must not expose credentials.
W2-D14-03 | Backend | Email | Email Monitoring Service | Build inbox polling and classification | 1. Polling loop: check inbox every N minutes; 2. Filter: has attachments (PDF/image); 3. Filter: sender whitelist patterns; 4. Download matching attachments to temp storage; 5. Classify: filename pattern + subject keyword matching; 6. Mark processed emails as read; 7. Track message IDs for dedup | P1-High | W2-D14-02 |  | Medium | Both | Polls inbox on schedule; downloads relevant attachments; classifies correctly; marks as read; dedup works | No | No
W2-D14-04 | Backend | Email | Email-to-Rounding-Sheet Pipeline | Auto-create rounding sheets from email attachments | 1. Detected rounding sheet attachment -> store encrypted in document storage; 2. Trigger OCR extraction (reuse Day 11-12 service); 3. Create rounding sheet record with status Draft; 4. Log to activity (Auto-Ingested from Email); 5. Non-matching emails: skip and log; 6. Background scheduler (APScheduler) | P0-Critical | W2-D14-03;W2-D11-04;W1-D3-07 |  | High | Both | Email with rounding sheet -> auto-creates Draft sheet with OCR data; appears in Rounding Sheet list; activity logged | No | Yes | CHECKPOINT: Full email pipeline working. Send test email -> verify sheet appears in app.
W3-D15-01 | Backend | Email | Email Agent Error Handling | Robustness for production email processing | 1. OCR fails -> create sheet with OCR Failed flag allow manual entry; 2. Corrupt attachment -> skip log with details; 3. Duplicate email -> dedup by message ID skip silently; 4. Token expired -> auto-refresh; 5. Network timeout -> exponential backoff (max 3 retries); 6. Dead-letter table for failed emails; 7. Status tracking: processed failed skipped | P1-High | W2-D14-04 |  | Medium | Manual Review | Every error scenario handled gracefully; no crashes; dead letters logged; status tracking accurate | No | No
W3-D15-02 | Backend | Agent Flow | Agent Status API | GET /api/agent/status for pipeline monitoring | 1. Return: connected providers last_check_time processed_today processed_week success_count failure_count skipped_count last_error; 2. Query email processing logs and agent_config | P1-High | W2-D14-04 |  | Low | Vibe-Code | Status endpoint returns real metrics; counts match actual processing | No | No
W3-D15-03 | Frontend | Agent Flow | Wire Agent Flow to Real Status | Update visualization with real pipeline data | 1. Provider cards show real connected/disconnected status; 2. Pipeline step nodes show real processing counts; 3. Poll status endpoint periodically; 4. Show last error if any | P2-Medium | W3-D15-02 |  | Low | Vibe-Code | Agent Flow page shows real data; status indicators reflect actual state | No | No
W3-D15-04 | Frontend | Config | Email Agent Configuration Page | Build config UI for email monitoring settings | 1. Outlook connection status indicator; 2. Test Connection button; 3. Monitoring interval setting; 4. Sender whitelist (editable list); 5. Subject keyword filters; 6. Enable/Disable toggle; 7. Store in agent_config table; 8. GET PUT /api/agent/config | P1-High | W3-D15-02 |  | Low | Vibe-Code | Config page functional; test connection works; settings persist; enable/disable controls agent | No | No
W3-D16-01 | Backend | HIPAA | Verify TDE Encryption | Confirm SQL Server encryption at rest is active | 1. Query sys.dm_database_encryption_keys; 2. Verify encryption_state = 3; 3. Backup encryption certificate; 4. Store cert backup securely; 5. Document recovery procedure | P0-Critical | W1-D3-01 |  | High | Manual Review | TDE confirmed active; certificate backed up; recovery procedure documented | Yes | No
W3-D16-02 | Backend | HIPAA | PHI Encryption Verification | Verify application-level PHI encryption is working | 1. Query patients table directly via SSMS; 2. Confirm name dob mrn columns contain ciphertext not plaintext; 3. Test key rotation (encrypt with v2 key decrypt v1 still works); 4. Verify API returns decrypted values correctly | P0-Critical | W1-D3-02 |  | High | Manual Review | Raw DB values are unreadable ciphertext; API returns correct plaintext; key rotation works | Yes | No | DO THIS MANUALLY. Inspect raw database values. If you see plaintext PHI encryption is broken.
W3-D16-03 | Backend | HIPAA | Document Encryption Verification | Verify files are encrypted at rest | 1. Check stored files on filesystem; 2. Attempt to open directly (should be unreadable); 3. Verify API decrypts and streams correctly; 4. Test with PDF and image files | P0-Critical | W1-D3-07 |  | High | Manual Review | Files on disk are encrypted binary; API serves correct content; both PDF and images work | Yes | No
W3-D16-04 | Backend | HIPAA | Audit Trail - PHI Read Logging | Ensure all PHI reads are logged not just writes | 1. Add read logging for: patient lookup patient detail encounter detail billing detail; 2. Verify audit entries created for every GET that returns PHI; 3. Include user_id and record_id in audit entry | P0-Critical | W1-D3-03 |  | High | Manual Review | Every API call that reads PHI creates an audit entry; verified by checking audit_trail after test flow | Yes | No | HIPAA requires logging reads not just writes. This is commonly missed.
W3-D16-05 | Backend | HIPAA | Audit Trail Immutability Verification | Verify audit_trail cannot be modified or deleted | 1. Attempt UPDATE on audit_trail -> should fail; 2. Attempt DELETE on audit_trail -> should fail; 3. Verify trigger error message is clear; 4. Test via API and direct SQL | P0-Critical | W1-D2-13 |  | High | Manual Review | UPDATE fails with error; DELETE fails with error; trigger active and working | Yes | No
W3-D16-06 | Backend | HIPAA | Document Access Audit | Log every document view separately | 1. Add audit entry for every GET /api/documents/{id}; 2. Include: user_id document_id patient_id timestamp ip_address; 3. Separate from general audit for easy document access review | P1-High | W1-D3-08;W1-D3-03 |  | Medium | Manual Review | Every document view creates audit entry; entries include all required fields | Yes | No
W3-D16-07 | Backend | HIPAA | Session Security Configuration | Configure Keycloak timeouts and API rate limiting | 1. Keycloak: 15min idle timeout 8hr max; 2. Brute force: lock after 5 failures; 3. API rate limiting: 100 req/min per user 10/min for login (slowapi); 4. HTTPS redirect; 5. Security headers: HSTS X-Frame-Options X-Content-Type CSP | P0-Critical | W1-D2-02;W1-D1-04 |  | Medium | Manual Review | Sessions expire correctly; brute force locks; rate limits enforced; HTTPS only; headers present | Yes | No
W3-D17-01 | Backend | HIPAA | RBAC Enforcement - All Endpoints | Apply role checks to every API endpoint | 1. Map roles to endpoints (see Day 17 plan table); 2. Add require_role to every router; 3. Test each endpoint with each role; 4. Verify 403 for unauthorized access; 5. Document role-endpoint matrix | P0-Critical | W1-D2-06 |  | High | Manual Review | Every endpoint has role check; wrong role returns 403; no unprotected endpoints; matrix documented | Yes | No | Test EVERY endpoint with EVERY role. This is systematic and tedious but critical.
W3-D17-02 | Backend | HIPAA | Data Minimization & Export Controls | Strip unauthorized fields and track exports | 1. Response serializers strip fields by role; 2. All CSV exports logged with: user module row_count filter_criteria timestamp; 3. Break-the-glass audit for out-of-workflow access; 4. Keycloak password policy: 12 chars complexity 90-day rotation | P1-High | W3-D17-01 |  | Medium | Manual Review | Billers don't see coding notes; all exports audit-logged; password policy enforced | Yes | No
W3-D17-03 | Frontend | HIPAA | Frontend Security Hardening | Remove PHI leaks and add role-based UI | 1. Remove ALL console.log that could leak PHI; 2. Auto-logout on idle (match 15min timeout); 3. Hide nav items and buttons by user role; 4. Error messages never expose internals; 5. CSP headers prevent XSS; 6. Verify parameterized queries (no SQL injection) | P0-Critical | W3-D17-01;W2-D10-04 |  | High | Manual Review | No console.log with PHI; auto-logout works; role-based UI hiding works; error messages generic; CSP active | Yes | No | Search codebase for console.log. Test auto-logout by waiting 15 minutes.
W3-D18-01 | Backend | Config | Reference Data CRUD APIs | CRUD for Clients Facilities Providers APRNs Users | 1. CRUD endpoints for each entity; 2. Soft-delete (deactivate not delete); 3. Facility linked to Client; 4. APRN linked to Provider; 5. Search on each entity | P1-High | W1-D1-08 |  | Low | Vibe-Code | All CRUD operations work; soft-delete deactivates; relationships maintained; search works | No | No
W3-D18-02 | Backend | Config | Seed Production Reference Data | Replace mock data with real values | 1. Seed clients facilities providers APRNs; 2. Import CPT codes from CMS files to cpt_codes table; 3. Import ICD-10 codes with HCC flags to icd10_codes table; 4. Build search endpoints: GET /api/cpt/search GET /api/icd10/search (max 10 results) | P1-High | W3-D18-01 |  | Medium | Manual Review | Real reference data in DB; CPT search finds codes; ICD-10 search finds codes with HCC info; no mock data | No | No
W3-D18-03 | Frontend | Config | Build Configuration CRUD Pages | Manage Clients Facilities Providers APRNs Users pages | 1. Each page: searchable table + add/edit dialog; 2. Follow Rounding Sheets table pattern; 3. Manage Clients; 4. Manage Facilities (linked to client); 5. Manage Providers; 6. Manage APRNs (linked to provider); 7. Manage Users (Keycloak integration) | P1-High | W3-D18-01;W1-D7-03 |  | Low | Vibe-Code | All 5 config pages work; CRUD operations save; relationships maintained; search works | No | No | Good candidate for Agent Terminal 2 - repetitive UI pattern x5
W3-D18-04 | Frontend | Config | Billing Codes & AQ Koder Config Pages | Build reference browser and AI config page | 1. Billing Codes: CPT/ICD-10 reference browser (search filter view - read only); 2. AQ Koder Config: connection status indicator test connection button configurable params (if any); 3. Wire to APIs | P2-Medium | W3-D18-02;W2-D13-01 |  | Low | Vibe-Code | Billing codes searchable and viewable; AQ Koder shows connection status; test connection works | No | No
W3-D19-01 | Testing | All | End-to-End Flow Test | Complete lifecycle walkthrough with real data | 1. Email agent receives rounding sheet; 2. Rounding Sheets: review OCR correct values verify; 3. Upload: select sheet fill fields check history submit; 4. Coding: TAKE analyze review 4 sections apply; 5. Billing: review mark billed or query; 6. Queries: check flagged; 7. History: see full trail; 8. Activity Log: verify all actions logged | P0-Critical | All Week 1-2 tasks |  | High | Manual Review | Complete lifecycle works end-to-end with real rounding sheets; every module functional; all data persists correctly | No | Yes | Use real sample rounding sheets. Document EVERY bug found.
W3-D19-02 | Testing | All | Bug Fix Sprint | Fix all bugs found in morning testing | 1. Prioritize: data loss > wrong calculations > broken workflows > UI glitches > cosmetic; 2. Fix each bug; 3. Re-test immediately after fix; 4. Document any bugs deferred to Week 4 | P0-Critical | W3-D19-01 |  | Medium | Both | All P0 and P1 bugs fixed; P2 bugs documented for Week 4 | No | No
W3-D19-03 | Testing | All | Performance Testing | Verify response times with realistic data volumes | 1. History: 4000+ rows pagination < 2 seconds; 2. Billing: 400+ rows acceptable; 3. Activity log: 100K+ entries performant; 4. Add DB indexes: client_id facility_id dos status patient_name mrn; 5. Add indexes: activity_log(timestamp module user_id); 6. Consider keyset pagination for large tables | P1-High | W3-D19-01 |  | Medium | Both | All pages load within 2 seconds; large datasets paginate efficiently; indexes created | No | No
W3-D20-01 | Testing | All | Error Handling Audit | Test every failure scenario | 1. API down -> friendly error page; 2. File upload fails -> error toast + retry; 3. OCR garbage -> low confidence let user correct; 4. AQ Coder timeout -> retry button; 5. Token expired -> silent refresh or redirect; 6. SQL connection lost -> 503 + retry; 7. Concurrent edit -> warning message | P1-High | W3-D19-02 |  | Medium | Both | Every error scenario shows user-friendly message; no white screens; no raw errors exposed | No | No
W3-D20-02 | Frontend | All | UI Polish Pass | Loading states empty states validation toast notifications | 1. Loading skeletons on ALL pages; 2. Empty states for all tables; 3. Form validation matches prototype; 4. Toast notifications for all actions; 5. Status chip colors correct; 6. Progress bars calculate correctly; 7. Pagination resets on filter change; 8. Document viewer zoom/pan/thumbnails work | P2-Medium | W3-D19-02 |  | Low | Vibe-Code | No blank loading screens; all empty states show messages; all forms validate; toasts show; viewers work | No | No
W3-D20-03 | Testing | All | CSV Export Verification | Verify all exports work with real data | 1. Activity Log export - correct columns formatted timestamps; 2. Queries export - correct columns all fields; 3. History export - 4000+ rows clean export; 4. All exports audit-logged with row count; 5. PHI in exports tracked | P1-High | W3-D19-02 |  | Low | Both | All exports download correctly; columns match; large exports work; all logged in audit trail | Yes | No
W3-D21-01 | Infrastructure | Deployment | Service Configuration | Set up production services | 1. FastAPI: systemd/Docker behind Gunicorn/Uvicorn workers; 2. Email agent: separate service with auto-restart; 3. Keycloak: systemd/Docker; 4. Process monitoring and auto-restart on crash | P0-Critical | All prior tasks |  | Medium | Both | All services start and run; auto-restart works; process monitoring active | No | No
W3-D21-02 | Infrastructure | Deployment | Nginx Reverse Proxy + HTTPS | Configure Nginx with TLS | 1. Install Nginx; 2. TLS cert (Let's Encrypt or org cert); 3. Proxy /api/ to FastAPI; 4. Serve React build on /; 5. Proxy /auth/ to Keycloak; 6. HTTP -> HTTPS redirect; 7. Security headers | P0-Critical | W3-D21-01 |  | Medium | Manual Review | HTTPS works; all routes proxied correctly; HTTP redirects; headers present; React app loads in production | Yes | No
W3-D21-03 | Infrastructure | Deployment | Environment & Backup Configuration | Secure secrets and automated backups | 1. .env file with all secrets (never in git); 2. Verify .gitignore includes .env; 3. Automated daily DB backup script; 4. Backup retention policy; 5. Test backup + restore | P0-Critical | W3-D21-01 |  | High | Manual Review | .env not in git; backups run; restore tested and verified | Yes | No
W3-D21-04 | Testing | All | Full Regression Test on Fresh DB | Complete test with clean state | 1. Fresh database (no dev data); 2. Fresh user accounts (one per role); 3. Test role restrictions for each role; 4. Test email agent with real email; 5. Test OCR with real samples; 6. Test AQ Coder with real analysis; 7. Verify audit_trail entries; 8. Verify encryption (check raw DB) | P0-Critical | W3-D21-01;W3-D21-02 |  | High | Manual Review | Everything works on clean state; roles enforced; email agent processes; OCR extracts; AI analyzes; audit complete; encryption verified | Yes | Yes | FINAL REGRESSION. If this passes the system is ready for Week 4 testing.
W3-D21-05 | Documentation | All | Build React for Production | Create production frontend bundle | 1. npm run build; 2. Verify production bundle works; 3. Deploy to Nginx static serving; 4. Test all pages in production mode; 5. Verify no dev-only code in production | P0-Critical | W3-D21-02 |  | Low | Vibe-Code | Production build succeeds; all pages work; no console errors; no dev tools | No | No
W3-D21-06 | Documentation | All | Deployment Runbook | Document operations procedures | 1. How to start/stop/restart each service; 2. How to view logs; 3. How to run database migrations; 4. How to rotate encryption keys; 5. How to restore from backup; 6. Known issues and limitations; 7. Test accounts and credentials | P1-High | W3-D21-04 |  | Low | Vibe-Code | Runbook covers all operations; another person could deploy following it | No | No
W3-D21-07 | Documentation | All | Handoff Package for Week 4 | Prepare testing phase materials | 1. Document known issues; 2. Document 90%-done features; 3. Create test accounts for each role; 4. Test scenario checklist for QA; 5. Bug report template | P1-High | W3-D21-04 |  | Low | Vibe-Code | Complete handoff package; QA team can start testing independently | No | Yes | FINAL MILESTONE: System ready for dedicated testing week.

## Day 4
Day 4 — Encounters + Patients API
Week 1 ¦ Tuesday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Encounters API | In Progress
2 | Midday — 3 hrs | Patients API + History Lookup | Not Started
3 | Afternoon — 4 hrs | Frontend: Replace Login with Keycloak | Not Started

## Day 3
Day 3 — HIPAA Foundation + Rounding Sheets API
Week 1 ¦ Monday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 3 hrs | HIPAA Middleware Layer | Not Started
2 | Midday — 4 hrs | Rounding Sheets CRUD API | Completed | Show the ocr extracted data in the database via API
3 | Afternoon — 4 hrs | Document Upload API | Completed | Storage Discussion - which type of storage we will be using, and how we will be securing it ? Currently I am building on local encrypted file system, but it is pluggable to other storage system and encryption types. | Disucss on approach of Fuzzy Mapping and Confidence Threshold, discuss its alternative with vectors. Show the prompt
4 | Morning — 3 hrs | Auth and Audit Middleware Layer | Completed
| Question | Models not populating in OpwnWebUI
Writing DB SCript for OCR's

## Day 2
Day 2 — Authentication (Keycloak) + Remaining Schema
Week 1 ¦ Sunday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Keycloak Setup | Completed
2 | Midday — 3 hrs | FastAPI + Keycloak Integration | Completed
3 | Afternoon — 4 hrs | Database Schema — Phase 2 | Completed

## Day 1
Day 1 — Environment & Database Setup
Week 1 ¦ Saturday ¦ ~10 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 3 hrs | SQL Server Setup | Completed
2 | Morning — 3 hrs | FastAPI Project Scaffold | Completed
3 | Afternoon — 4 hrs | Database Schema — Phase 1 | Completed

## Day 5
Day 5 — Upload + Coding APIs
Week 1 ¦ Wednesday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Upload API | Not Started
2 | Midday — 4 hrs | Coding API | Not Started
3 | Afternoon — 3 hrs | Coding API — H&P Inheritance + Advanced | Not Started

## Day 6
Day 6 — Billing + Queries APIs
Week 1 ¦ Thursday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Billing API | Not Started
2 | Midday — 3 hrs | Queries API | Not Started
3 | Afternoon — 4 hrs | History + Activity Log APIs | Not Started

## Day 7
Day 7 — Dashboard API + Frontend Migration Starts
Week 1 ¦ Friday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 3 hrs | Dashboard API | Not Started
2 | Midday — 4 hrs | Frontend: API Service Layer | Not Started
3 | Afternoon — 4 hrs | Frontend: Migrate Rounding Sheets | Not Started

## Day 8
Day 8 — Rounding Sheet Detail + Upload Migration
Week 2 ¦ Saturday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Migrate RoundingSheetDetailV2 | Not Started
2 | Midday — 4 hrs | Migrate UploadV2 | Not Started
3 | Afternoon — 3 hrs | Upload Migration Continued | Not Started

## Day 9
Day 9 — Coding + Billing Migration
Week 2 ¦ Sunday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Migrate CodingV2 | Not Started
2 | Midday — 4 hrs | Migrate EncountersV2 Workspace | Not Started
3 | Afternoon — 3 hrs | Migrate BillingV2 + BillingDetailV2 | Not Started

## Day 10
Day 10 — Queries, History, Activity Log, Dashboard Migration
Week 2 ¦ Monday ¦ ~10 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 3 hrs | Migrate Queries | Not Started
2 | Midday — 3 hrs | Migrate History + Activity Log | Not Started
3 | Afternoon — 4 hrs | Migrate Dashboard + Final Auth Polish | Not Started

## Day 11
Day 11 — Tesseract OCR Integration
Week 2 ¦ Tuesday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | OCR Service Setup | Not Started
2 | Midday — 4 hrs | Structured Field Extraction (Zone-Based) | Not Started
3 | Afternoon — 3 hrs | OCR API Endpoint | Not Started

## Day 12
Day 12 — OCR Polish + Handwritten Handling
Week 2 ¦ Wednesday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Handwritten Detection + Handling | Not Started
2 | Midday — 3 hrs | OCR Results → UI Flow | Not Started
3 | Afternoon — 4 hrs | Encounter Generation from OCR | Not Started

## Day 13
Day 13 — AQ Coder Integration
Week 2 ¦ Thursday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | AQ Coder API Bridge | Not Started
2 | Midday — 4 hrs | Wire AQ Coder to Encounters Flow | Not Started
3 | Afternoon — 3 hrs | AQ Coder Results Persistence | Not Started

## Day 14
Day 14 — Email Agent Pipeline (Outlook)
Week 2 ¦ Friday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Microsoft Graph API Setup | Not Started
2 | Midday — 4 hrs | Email Monitoring Service | Not Started
3 | Afternoon — 3 hrs | Email → Rounding Sheet Pipeline | Not Started

## Day 15
Day 15 — Email Agent Polish + Agent Flow UI
Week 3 ¦ Saturday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Email Agent Robustness | Not Started
2 | Midday — 3 hrs | Agent Flow Page — Real Status | Not Started
3 | Afternoon — 4 hrs | Email Agent Configuration UI | Not Started

## Day 16
Day 16 — HIPAA Hardening (Day 1)
Week 3 ¦ Sunday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Encryption at Rest — Verification & Hardening | Not Started
2 | Midday — 4 hrs | Audit Trail Hardening | Not Started
3 | Afternoon — 3 hrs | Session Security | Not Started

## Day 17
Day 17 — HIPAA Hardening (Day 2) + Access Controls
Week 3 ¦ Monday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Role-Based Access Control (RBAC) | Not Started
2 | Midday — 3 hrs | Data Minimization + Export Controls | Not Started
3 | Afternoon — 4 hrs | Frontend Security | Not Started

## Day 18
Day 18 — Seed Data, Reference Data, Configuration Pages
Week 3 ¦ Tuesday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Reference Data APIs + Seeding | Not Started
2 | Midday — 4 hrs | Configuration Pages (Previously Placeholders) | Not Started
3 | Afternoon — 3 hrs | Billing Codes + AQ Coder Configuration | Not Started

## Day 19
Day 19 — Integration Testing + Bug Fixes
Week 3 ¦ Wednesday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | End-to-End Flow Testing | Not Started
2 | Midday — 4 hrs | Bug Fix Sprint | Not Started
3 | Afternoon — 3 hrs | Performance Check | Not Started

## Day 20
Day 20 — Edge Cases, Error Handling, Polish
Week 3 ¦ Thursday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Error Handling Audit | Not Started
2 | Midday — 4 hrs | UI Polish | Not Started
3 | Afternoon — 3 hrs | CSV Exports + Final Features | Not Started

## Day 21
Day 21 — Final Integration, Deployment Prep
Week 3 ¦ Friday ¦ ~11 hrs
# | Time Block | Task | Status | Remarks
1 | Morning — 4 hrs | Deployment Configuration | Not Started
2 | Midday — 4 hrs | Full Regression Test | Not Started
3 | Afternoon — 3 hrs | Handoff Prep for Week 4 Testing | Not Started